## Sheet1
|  |  |  | January |  |  |  | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
|  |  | % of Month filled | 45.4167 |  |  |  | 92.5 |  |  |  | 74.1667 |  |  |  | 78.75 |  |  |  | 114.5833 |  |  |  | 123.3333 |  |  |  | 93.75 |  |  |  | 82.9167 |  |  |  | 93.3333 |  |  |  | 71.25 |  |  |  | 54.5833 |  |  |  | 23.3333 |  |  |  | 45.4167 |  |  |  | 92.5 |  |  |  | 62.5 |  |  |  | 78.75 |  |  |  | 112.0833 |  |  |  | 121.25 |  |  |  | 93.75 |  |  |  | 82.9167 |  |  |  | 68.3333 |  |  |  | 82.0833 |  |  |  | 47.0833 |  |  |  | 18.3333
customer | interval months | Task name | estimated hours | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4 | week 1 | week 2 | week3 | week 4
|  | Totals |  | 54.5 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 88.5 | 6 | 0 | 0 | 137.5 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 112.5 | 0 | 0 | 0 | 99.5 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 85.5 | 0 | 0 | 0 | 65.5 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 54.5 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 90.5 | 4 | 0 | 0 | 134.5 | 0 | 0 | 0 | 145.5 | 0 | 0 | 0 | 112.5 | 0 | 0 | 0 | 99.5 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 98.5 | 0 | 0 | 0 | 56.5 | 0 | 0 | 0 | 22 | 0 | 0 | 0
Project work | bar: 93.3333 week 2; 71.25 week 1 to 71.25 week 2; 71.25 week 4 to 54.5833 week 1
Altora AG | 6 | test and tag | 8 | 45.4167 week 1: 8; 93.75 week 1: 8; 45.4167 week 1: 8; 93.75 week 1: 8
Aspire | 6 | Commericial Ducted Service | 4 | 78.75 week 1: 4; 71.25 week 1: 4; 78.75 week 1: 4; 82.0833 week 1: 4
Aspire | 12 | Split Deep clean | 8 | 54.5833 week 1: 8; 47.0833 week 1: 8
Aspire | 12 | RCD injection testing | 2 | 78.75 week 1: 2; 78.75 week 2: 2
Aspire | 12 | test and tag | 2 | 78.75 week 1: 2; 78.75 week 2: 2
Aspire | 12 | Emergency light Testing | 1 | bar: 74.1667 week 1; 78.75 week 1; 78.75 week 1
Cameo | 12 | Fridge/Freezer Servic | 3 | 123.3333 week 1: 3; 121.25 week 1: 3
Cameo | 12 | Split System Deep Clean | 20 | 74.1667 week 1: 20; 62.5 week 1: 20
CBM Facilities Group | 6 | emergecy Light test | 2 | 78.75 week 2: 2; 71.25 week 1: 2; 78.75 week 1: 2; 82.0833 week 1: 2
CBM Facilities Group | 12 | RCD Injection Tests | 4 | 78.75 week 2: 4; 78.75 week 1: 4
CBM Facilities Group | 6 | RCD Push Button tests | 2 | 71.25 week 1: 2; 82.0833 week 1: 2
CBM Facilities Group | 12 | Split Sytem Deep Clean | 4 | 123.3333 week 1: 4; 121.25 week 1: 4
CBM Facilities Group | 12 | Test and Tag | 2 | 82.9167 week 1: 2; 82.9167 week 1: 2
Clear Ridge Fabrication | 12 | Test and tag | 11 | 74.1667 week 1: 11; 62.5 week 1: 11
Evolution -Boundry st | 12 | cassette and Split Deep Clean (Dining/office) | 23 | 82.0833 week 1: 23
Evolution -Boundry st | 12 | Commercial Dryer | 9 | 93.3333 week 1: 9; 68.3333 week 1: 9
Evolution -Boundry st | 6 | Commercial Washer | 2 | 74.1667 week 1: 2; 62.5 week 1: 2
Evolution -Boundry st | 12 | Commercial Washer | 11 | 93.3333 week 1: 11; 68.3333 week 1: 11
Evolution -Boundry st | 6 | Commercical Dryer | 2 | 74.1667 week 1: 2; 62.5 week 1: 2
Evolution -Boundry st | 12 | Display Fridge Serivice inc Salad bars | 8 | 93.75 week 1: 8; 93.75 week 1: 8
Evolution -Boundry st | 6 | Display Fridge Service inc salad bars | 3 | 92.5 week 1: 3; 92.5 week 1: 3
Evolution -Boundry st | 12 | Ducted System clean and service-Dining Room | 4 | 93.75 week 1: 4; 93.75 week 1: 4
Evolution -Boundry st | 6 | emergency Light Testing | 4 | 92.5 week 1: 4; 82.9167 week 1: 4; 92.5 week 1: 4; 82.9167 week 1: 4
Evolution -Boundry st | 12 | Exhaust Fan Service kitchen/office and air curtains | 3 | 93.3333 week 1: 3; 68.3333 week 1: 3
Evolution -Boundry st | 12 | Exhuast Fan Service accomdation rooms? | 3 | 93.3333 week 1: 3; 68.3333 week 1: 3
Evolution -Boundry st | 3 | Fresh Water Booster Pump Service | 2 | 92.5 week 1: 2; 114.5833 week 1: 2; 82.9167 week 1: 2; 54.5833 week 1: 2; 92.5 week 1: 2; 112.0833 week 1: 2; 82.9167 week 1: 2; 47.0833 week 1: 2
Evolution -Boundry st | 12 | Fridge and Freezer Service | 4 | 93.3333 week 1: 4; 68.3333 week 1: 4
Evolution -Boundry st | 6 | Generator Service | 3 | 114.5833 week 1: 3; 54.5833 week 1: 3
Evolution -Boundry st | 12 | Ice cream freezer service | 1 | bar: 93.75 week 1; 93.75 week 1; 68.3333 week 1
Evolution -Boundry st | 3 | ice machine | 3.5 | 74.1667 week 1: 3.5; 123.3333 week 1: 3.5; 93.3333 week 1: 3.5; 23.3333 week 1: 3.5; 62.5 week 1: 3.5; 121.25 week 1: 1; 68.3333 week 1: 3.5; 18.3333 week 1: 3.5
Evolution -Boundry st | 12 | Ice Machines | 9 | 93.3333 week 1: 9
Evolution -Boundry st | 3 | Kitchen Cassette deep clean | 12 | 92.5 week 1: 12; 114.5833 week 1: 12; 82.9167 week 1: 12; 54.5833 week 1: 12; 92.5 week 1: 12; 112.0833 week 1: 12; 82.9167 week 1: 12; 47.0833 week 1: 12
Evolution -Boundry st | 12 | Oven Service | 16 | 93.75 week 1: 16; 93.75 week 1: 16
Evolution -Boundry st | 12 | RCD Injection Tests Acco+Games+Laundries+Laundry sub boards+Admin | 24 | 114.5833 week 1: 24; 112.0833 week 1: 24
Evolution -Boundry st | 12 | RCD push button Acco+Admin+Games+Laundries+sub boards | 12 | 54.5833 week 1: 12; 47.0833 week 1: 12
Evolution -Boundry st | 12 | Solar Panel Service | 4 | 114.5833 week 1: 4; 112.0833 week 1: 4
Evolution -Boundry st | 6 | Split Service Accomdation Rooms | 16 | 92.5 week 1: 16; 92.5 week 1: 16
Evolution -Boundry st | 12 | Split System Deep Clean Accomdation Rooms only | 60 | 82.9167 week 1: 60; 82.9167 week 1: 60
Evolution -Boundry st | 12 | Switchboard Service (not RCD) | 15 | 71.25 week 1: 15; 82.0833 week 1: 15
Evolution -Boundry st | 12 | test and tag rooms+admin+Kitchen+Games+all Laundys | 24 | 45.4167 week 1: 24; 45.4167 week 1: 24
Evolution -Boundry st | 24 | Washer/Dryer Service Laundry 1 | 30 | 93.3333 week 1: 30
Evolution -Boundry st | 6 | Washer/Dryer Service Laundry 1 | 10 | 74.1667 week 1: 10; 62.5 week 1: 10; 68.3333 week 1: 10
Evolution -Boundry st | 24 | Washer/Dryer Service Laundry 2 | 30 | 71.25 week 1: 18
Evolution -Boundry st | 6 | Washer/Dryer Service Laundry 2 | 6 | 78.75 week 1: 6; 78.75 week 1: 6; 82.0833 week 1: 6
Evolution -Boundry st | 24 | Washer/Dryer Service Laundry 3 | 30 | 71.25 week 1: 18
Evolution -Boundry st | 6 | Washer/Dryer Service Laundry 3 | 6 | 114.5833 week 1: 6; 112.0833 week 1: 6; 47.0833 week 1: 6
Evolution -Boundry st | 3 | Split system/cassette filter cleans | 3 | 78.75 week 1: 3; 78.75 week 1: 3
Evolution -Boundry st | 24 | Washer/Dryer Service Laundry 4 | 14 | 74.1667 week 1: 14
Evolution -Boundry st | 6 | Washer/Dryer Service Laundry 4 | 3 | 93.3333 week 1: 3
Evolution -Clubb Inn | 12 | Exhaust Fan Service | 4 | 93.3333 week 1: 4; 68.3333 week 1: 4
Evolution -Clubb Inn | 12 | RCD Injection Tests | 3 | 54.5833 week 1: 3; 47.0833 week 1: 3
Evolution -Clubb Inn | 12 | RCD Push Button Tests | 1 | bar: 114.5833 week 1; 112.0833 week 1
Evolution -Clubb Inn | 12 | Split System Deep Clean | 40 | 123.3333 week 1: 40; 121.25 week 1: 40
Evolution -Clubb Inn | 6 | Split System Service | 8 | 45.4167 week 1: 8; 45.4167 week 1: 8
Evolution -Clubb Inn | 12 | Switchboard Service (not RCD) | 6 | 71.25 week 1: 6; 82.0833 week 1: 6
Evolution -Clubb Inn | 12 | test and tag | 9 | 78.75 week 1: 9; 78.75 week 1: 9
Evolution -Clubb Inn | 1 | Washer/Dryer Service | 4.5 | 45.4167 week 1: 4.5; 92.5 week 1: 4.5; 74.1667 week 1: 4.5; 78.75 week 1: 4.5; 114.5833 week 1: 4.5; 123.3333 week 1: 4.5; 93.75 week 1: 4.5; 82.9167 week 1: 4.5; 93.3333 week 1: 4.5; 71.25 week 1: 4.5; 54.5833 week 1: 4.5; 23.3333 week 1: 4.5; 45.4167 week 1: 4.5; 92.5 week 1: 4.5; 62.5 week 1: 4.5; 78.75 week 1: 4.5; 112.0833 week 1: 4.5; 121.25 week 1: 4.5; 93.75 week 1: 4.5; 82.9167 week 1: 4.5; 68.3333 week 1: 4.5; 82.0833 week 1: 4.5; 47.0833 week 1: 4.5; 18.3333 week 1: 4.5
Evolution -Clubb Inn | 24 | Washer/Dryer Service | 19 | 54.5833 week 1: 18
Evolution -Mine Site | 12 | Automatic Coffee Machine Service | 30 | 93.75 week 1: 30; 93.75 week 1: 30
Evolution -Mine Site | 3 | Automatic Coffee Machine Service | 42 | 92.5 week 1: 42; 114.5833 week 1: 42; 71.25 week 1: 16; 92.5 week 1: 42; 112.0833 week 1: 42; 82.0833 week 1: 16
Evolution-Boundry Street | 12 | Outside Condenser Clean | 12 | 78.75 week 1: 12; 78.75 week 1: 12
French Hot Bread | 12 | Dishwasher Service | 3 | 123.3333 week 1: 3; 121.25 week 1: 3
Kurrajong Recycling | 12 | Evaporative AC Service | 2 | 82.9167 week 1: 2; 82.9167 week 1: 2
Kurrajong Recycling | 12 | Split System Deep Clean Park and recycling | 3.5 | 92.5 week 1: 3.5; 92.5 week 1: 3.5
LLAC | 12 | Evaporative Cooler Service-all sites | 5 | 92.5 week 1: 5; 92.5 week 1: 5
LLAC | 12 | RCD injection testing-all sites | 4 | 92.5 week 1: 4; 92.5 week 1: 4
LLAC | 12 | Smoke alarm Testing-all sites | 2 | 92.5 week 1: 2; 92.5 week 1: 2
LLAC | 12 | Split System Deep Cleans all sites | 6 | 92.5 week 1: 6; 92.5 week 1: 6
Meals on Wheels | 12 | fridge and freezer Service | 3 | 114.5833 week 1: 3; 112.0833 week 1: 3
Mid West | 12 | Split System Deep Clean | 5 | 92.5 week 1: 5; 92.5 week 1: 5
Mid West | 3 | Test and Tag | 14 | 74.1667 week 1: 14; 123.3333 week 1: 14; 93.3333 week 1: 14; 23.3333 week 1: 14; 62.5 week 1: 14; 121.25 week 1: 14; 68.3333 week 1: 14; 18.3333 week 1: 14
MLAHMC | 12 | Evaporative AC Service accross all sites | 12 | 78.75 week 1: 12; 78.75 week 1: 12
MLAHMC | 12 | RCD Injection Tests-All sites | 5 | 82.9167 week 1: 5; 82.9167 week 1: 5
MLAHMC | 12 | Smoke Alarm Testing accross sites | 5 | 82.9167 week 1: 5; 82.9167 week 1: 5
MLAHMC | 12 | Split System Deep Clean | 12 | 78.75 week 1: 12; 78.75 week 1: 12
Mt Mulga | 6 | Emergency Light Testing | 2 | 74.1667 week 1: 2; 93.3333 week 1: 2; 62.5 week 1: 2; 68.3333 week 1: 2
Mt Mulga | 12 | RCD testing | 2 | 93.3333 week 1: 2; 68.3333 week 1: 2
Mt Mulga | 24 | Split System | 2 | 68.3333 week 1: 2
Mt Mulga | 12 | Test and Tag | 4 | 93.3333 week 1: 4; 68.3333 week 1: 4
O-Connors | 12 | Split System Air Conditioner Deep Clean | 3 | 45.4167 week 1: 3; 45.4167 week 1: 3
RFBI | 12 | Ducted System clean and service | 20 | 114.5833 week 1: 20; 112.0833 week 1: 20; 82.0833 week 1: 20
RFBI | 6 | Ducted system-filter cleans | 3 | 54.5833 week 1: 3; 47.0833 week 1: 3
RFBI | 6 | Emergency Light Testing | 3 | 45.4167 week 1: 3; 93.75 week 1: 3; 45.4167 week 1: 3; 93.75 week 1: 3
RFBI | 12 | Exhause Fan Service | 4 | 123.3333 week 1: 4; 121.25 week 1: 4
RFBI | 3 | Filter Cleans -all acs | 6 | 74.1667 week 1: 6; 123.3333 week 1: 6; 93.3333 week 1: 6; 23.3333 week 1: 6; 62.5 week 1: 6; 121.25 week 1: 6; 68.3333 week 1: 6; 47.0833 week 1: 6
RFBI | 12 | Ice machine service | 2 | 92.5 week 1: 2; 92.5 week 1: 2
RFBI | 12 | Injection test | 10 | 93.75 week 1: 10; 93.75 week 1: 10
RFBI | 6 | RCD Push button Tests | 4 | 45.4167 week 1: 4; 45.4167 week 1: 4
RFBI | 12 | Solar Panel Service | 3 | 82.9167 week 1: 3; 82.9167 week 1: 3
RFBI | 12 | Split System Deep clean Banksia Wing only | 24 | 123.3333 week 1: 24; 121.25 week 1: 24
RFBI | 12 | Split System Deep Clean Cooee Wing Only | 42 | 123.3333 week 1: 42; 121.25 week 1: 42
RFBI | 12 | Split System Deep Clean Garden Wing Only | 21 | 78.75 week 1: 21; 78.75 week 1: 21
RFBI | 12 | Split System Deep Clean KITCHEN/Laundry/Server rooms and Offices | 28 | 93.75 week 1: 28; 93.75 week 1: 28
RFBI | 12 | Split System Deep Clean Staff Rooms and dongas | 16 | 114.5833 week 1: 16; 112.0833 week 1: 16
RFBI | 12 | Switchboard Service (not RCD) | 16 | 78.75 week 1: 16; 78.75 week 1: 16
RFBI | 3 | Temp Probe Calibrations | 4 | 45.4167 week 1: 4; 78.75 week 1: 4; 93.75 week 1: 4; 71.25 week 1: 4; 45.4167 week 1: 4; 78.75 week 1: 4; 93.75 week 1: 4; 82.0833 week 1: 4
RFBI | 12 | Test and Tag | 38 | 92.5 week 1: 38; 92.5 week 1: 38
RFBI | 12 | Outside Condenser Clean | 16 | 78.75 week 1: 16; 78.75 week 1: 16
RFBI-rented houses | 12 | General Electrical Check | 1 | bar: 78.75 week 1; 78.75 week 1
RFBI-rented houses | 12 | RCD injection tests | 2 | 71.25 week 1: 2; 82.0833 week 1: 2
RFBI-rented houses | 6 | RCD Push button tests | 1 | bar: 78.75 week 1; 78.75 week 1
RFBI-rented houses | 12 | Smoke alarm testing | 1 | bar: 78.75 week 1; 62.5 week 1; 78.75 week 1
RFBI-rented houses | 12 | Split System Deep Clean | 4 | 74.1667 week 1: 4; 62.5 week 1: 4
RFBI-rented houses | 6 | split system service | 1 | bar: 78.75 week 1; 78.75 week 1; 82.0833 week 1
RFBI-rented houses | 12 | Test and tag | 2 | 78.75 week 1: 2; 78.75 week 1: 2
SGS | 12 | test and tag | 10 | 78.75 week 1: 10; 78.75 week 1: 10
Solterra | 12 | Split System Deep Clean | 4 | 78.75 week 1: 4; 78.75 week 1: 4
Solterra | 12 | test and tag | 6 | 78.75 week 1: 6; 78.75 week 1: 6
Solterra | 12 | Smoke Alarm Testing | 5 | bar: 78.75 week 1; 93.3333 week 1; 78.75 week 1
Solterra | 12 | RCD Injection tests | 4 | 78.75 week 1: 4; 78.75 week 1: 4
Solterra | 6 | RCD Push button Tests | 2 | 71.25 week 1: 2; 68.3333 week 1: 2
Tivolli | 12 | Commercial Air Conditioner Service | 4 | 114.5833 week 1: 4; 112.0833 week 1: 4
Tivolli | 12 | Fridge and Freezer Service | 2 | 114.5833 week 1: 2; 112.0833 week 1: 2
Tivolli | 12 | Split System Deep Clean | 2 | 114.5833 week 1: 2; 112.0833 week 1: 2
Kurrajong Living Life style | 24 | Split System Deep Clean | 3.5 | 78.75 week 1: 3.5
SGS | 12 | Split System Deep Clean | 6 | 114.5833 week 1: 6; 112.0833 week 1: 6
SGS | 12 | injection testing | 4 | 93.75 week 1: 4; 93.75 week 1: 4
Meals on Wheels | 12 | split system clean | 1 | bar: 78.75 week 1; 93.75 week 1; 92.5 week 2; 78.75 week 1; 93.75 week 1